Week 4 Prepare

Scenario 1: WestConnex Motorway, Australia

Agtivity 1-Behaviour Over Time Graph

At launch, WestConnex was presented as a major motorway network costing approximately A 10billion Earlybusiness — caseestimates were approximately -         A$11-11.5 billion, with a roughly ten-year delivery program. Later estimates increased to approximately A$16.8-17 billion, excluding some additional network-integration works.The network opened in stages, with the final Rozelle Interchange opening in November 2023.

| Year | Planned comulative completion | Illustrative actual completion |
| --- | --- | --- |
| 2012 | 0% | 0% |
| 2015 | 15% | 10% |
| 2017 | 35% | 25% |
| 2019 | 60% | 45% |
| 2021 | 80% | 68% |
| 2023 | 100% | 100% |

The planned line would normally be S-shaped: a slow start during design and approvals, rapid progress during construction, and a slower final stage during testing and integration. The actual line would initially follow the plan but begin to fall behind around 2014–2015, when scope, design, funding and delivery arrangements changed. The gap would then widen because tunnelling, property acquisition and network integration were highly interdependent.

The most important feature is not simply that the final network opened in 2023. It is that the project’s cost and scope expanded significantly while delivery became more complicated and staged.

Activity 2 — The Rework Cycle

The flow of planned work into work in progress was slowed by:

•	environmental approvals and community opposition;

•	property acquisition and relocation disputes;

•	difficult urban tunnelling conditions;

•	utility relocation and traffic-management requirements;

•	changes to scope and network connections;

•	coordination between government, contractors and concession partners.

A simple rework cycle is:

Planned work → Work in progress → Completed work

Completed-looking work → defects/design changes → rework → Work in progress

For WestConnex, work that appeared complete could return to rework when tunnel interfaces, road connections, utilities or safety requirements did not integrate correctly. Design changes could also require redesign, demolition, reconstruction or retesting.

Rework reduced the project’s effective completion rate because crews were spending time correcting previous work instead of producing new accepted work. This increased work in progress and extended the schedule.

Adding more staff or contractors could increase output only when tasks were independent and properly prepared. In tightly connected tunnel works, extra crews could create:

•	more handovers and communication requirements;

•	congestion in restricted work areas;

•	additional supervision and safety demands;

•	more chances for interface errors.

This illustrates Brooks’s Law: adding manpower to a late project can initially make it later. The principle comes from software development, so it is not a literal motorway rule, but the same systems effect can occur in complex construction projects. Targeted specialists may help, but simply increasing headcount does not remove design uncertainty, approval delays or coordination bottlenecks.

Scenario 2: Jakarta–Bandung High-Speed Rail, Indonesia

Activity 1 — Behaviour Over Time Graph

The project agreement was reached in 2015, construction began in 2016, and the railway was originally expected to operate in 2019. The planned cost was approximately US$5.5–6 billion, although reported figures vary depending on the exchange rate and cost baseline.

The railway opened commercially in October 2023. The final reported cost was approximately US$7.3-8billion, representing an over run of about, US$1.2 billion compared with earlier estimates.

| Year | Planned comulative completion | Illustrative actual completion |
| --- | --- | --- |
| 2015 | 0% | 0% |
| 2016 | 15% | 10% |
| 2017 | 40% | 22% |
| 2018 | 75% | 38% |
| 2019 | 100% | 50% |
| 2020 | 100% | 60% |
| 2021 | 100% | 73% |
| 2022 | 100% | 90% |
| 2023 | 100% | 100% |

The planned curve reaches 100% in 2019 and then becomes flat. The actual curve is a delayed S-curve: progress is slow during land acquisition and design, improves during construction, and then flattens because of COVID-19, unfinished stations, testing and system integration.

The clearest point of divergence was 2019, when the railway was supposed to open but remained incomplete. The delay was already developing before COVID-19 because of land-acquisition disputes, environmental concerns and engineering challenges.

Activity 2 — The Rework Cycle

The flow from planned work into work in progress was slowed by:

•	disputes over thousands of land parcels;

•	permitting and environmental requirements;

•	difficult terrain and tunnelling conditions;

•	changing designs and construction requirements;

•	financing and political disagreements between stakeholders;

•	COVID-19 restrictions and supply-chain disruption;

•	incomplete stations and connecting infrastructure.

The rework cycle can be described as:

Planned railway work → WIP → completed structures and systems

Defects, geological surprises or design changes → rework → WIP

For example, unexpected ground conditions could require tunnel redesign or additional stabilisation. Land-access problems could leave construction crews waiting or force the sequence of work to change. Interfaces between tracks, signalling, stations and trains could reveal defects during testing, sending apparently completed work back into rework.

The result is that gross activity does not equal usable completion. The project may have many active workers and visible construction while the amount of railway that is safe, tested and operational remains much lower.

Adding staff could increase capacity only if work packages were independent and the necessary land, materials and designs were available. If the project was already congested, additional workers could increase communication costs, supervision requirements and interface errors.

The feedback loop was:

Delay → pressure to work faster → more parallel work and late decisions → defects and interface conflicts → rework → slower net completion → further delay

A balancing response would be to complete land acquisition before releasing work, freeze designs earlier, use specialist teams for difficult tunnels, and require integration testing before declaring work complete.

Scenario 3: Nusantara New Capital City, Indonesia

Activity 1 — Behaviour Over Time Graph

Nusantara was announced in 2019. The overall investment requirement has commonly been estimated at approximately US$30–35 billion, although estimates differ according to the project scope and date.

The development plan has five stages extending from 2022 to 2045. Phase I was intended to deliver basic infrastructure, the presidential complex, government buildings and accommodation. The political centre was expected to begin operating around August 2024.

The guide reports that only about 15% of planned works had been completed by August 2024. This should be treated as an approximate progress indicator rather than a precise measurement of every construction package.

| Milestone | Planned completion toward the 2024 operating milestone | Illustrative actual completion |
| --- | --- | --- |
| 2019 announcement | 0% | 0% |
| 2022 start of Phase I | 20% | 5% |
| 2023 | 60% | 10% |
| August 2024 | 100% | Approximately 15% |

This BOTG should be understood as measuring progress toward the initial operating milestone, not completion of the entire city. Full development is planned to continue in stages through 2045.

The actual curve is much flatter than planned. Some flagship buildings were progressing, but enabling systems such as water, electricity, roads, housing and airport access were not sufficiently complete to support a functioning capital city. The intended move was therefore postponed, and later political targets were revised.

Activity 2 — The Rework Cycle

The movement of planned work into work in progress was slowed by:

•	heavy rainfall and difficult construction conditions;

•	funding gaps and limited realisation of private investment;

•	uncertainty following changes in political leadership;

•	resignations of senior officials in the Nusantara authority;

•	incomplete water, electricity and waste systems;

•	access and airport delays;

•	land, environmental and Indigenous-community concerns;

•	limited population density and uncertainty about future demand.

The rework cycle was:

Planned city works → WIP → completed buildings and infrastructure

Design changes, incomplete interfaces or changed priorities → rework → WIP

A building can appear physically complete but still not be operational if roads, electricity, water, telecommunications or public services are unfinished. This means that construction progress may be reported while usable completion remains low.

The main reinforcing loop was:

Incomplete infrastructure → delayed relocation and low occupancy → weak investor confidence → less private funding → slower construction → more incomplete infrastructure

Another loop was:

Schedule pressure → rushed construction and parallel work → defects and integration problems → rework → reduced productivity → further delay

Adding workers would not automatically solve the problem. If utilities, materials, land access or design decisions were missing, more workers could create site congestion and additional coordination requirements. Brooks’s Law applies here as an analogy: adding people to a late and tightly coupled project can initially reduce productivity. However, specialist teams could still help where work packages were genuinely independent and ready to proceed.

Wrap-up Reflection

The statement “structure drives behaviour” means that project outcomes are shaped not only by individual effort, but also by the relationships, delays, incentives, information flows and feedback loops built into the project system.

For megaproject management, this means:

- Planning must include dependencies, approvals, land access, learning, testing and rework—not only the original schedule.

- Managers should measure accepted and usable completion, not just activity or the number of workers on site.

- Work in progress, defects and rework should be monitored because they can reveal future delays before the final deadline is missed.

- When a project falls behind, managers should investigate the structure causing the problem rather than automatically adding staff or overtime.

- Design changes and interfaces between contractors should be managed early.

- Funding, political confidence and public support should be treated as part of the project system because they influence the flow of work.

- Recovery strategies should be tested for unintended effects, such as increasing congestion, errors and rework.

The main lesson is that working harder does not guarantee better results. If the project structure creates bottlenecks and feedback loops, additional effort may increase activity without increasing net completion.

Useful references include:

•	https://www.audit.nsw.gov.au/our-work/reports/westconnex-changes-since-2014

•	https://www.transurban.com/news/rozelle-interchange-opening

•	https://www.lowyinstitute.org/the-interpreter/indonesia-high-cost-high-speed-rail

•	https://railwaynews.net/jakarta-bandung-high-speed-rail-cost-overruns-challenges.html

•	https://apnews.com/article/indonesia-southeast-asia-highspeed-railway-e7a53ecbcb077b4403d9232e7b93bcf3

•	https://www.iseas.edu.sg/articles-commentaries/iseas-perspective/2024-59-the-nusantara-project-in-progress-risks-and-challenges-by-siwage-dharma-negara-and-neo-hui-yun-rebecca/

The guide also mentions “Focus Question 5,” but it does not include the actual question. That question would need to be provided separately to answer it accurately.