PMGT1852 Week 03

PMGT1852 Week 03 - Stakeholder Analysis Framework: Identification, Assessment and Prioritisation

Overview

This week turns the stakeholder concept into a working method. The analysis framework has three steps - identification, assessment, prioritisation - and each step has its own tools:

•	The purpose of stakeholder analysis: why analyse at all, and what a good analysis decides.

•	The three-step framework: identification, assessment, prioritisation (and then engagement).

•	Help-harm potential: how much a stakeholder could help, and how much they could harm, the project.

•	Two assessment grids: the potential matrix and the commitment matrix.

•	CATWOE for reading a stakeholder's situation and worldview.

•	MoSCoW for prioritising what must be addressed first.

Key Concepts

The purpose of stakeholder analysis

Stakeholder analysis exists to turn an overwhelming list of people into a defensible allocation of attention. It answers three questions: who matters, why they matter, and in what order their needs, risks and contributions must be handled. Without it, engagement effort is spread evenly over uneven stakes, and the loudest stakeholder sets the agenda instead of the most consequential one.

The three-step framework

- Identification: define the boundary of the system of concern, then list the stakeholders inside it. Disaggregate aggregated labels ("the community", "the regulators") into distinct groups with distinct roles, contributions and impacts.

- Assessment: characterise each stakeholder - their interests and expectations, their roles and contributions, and how they could help or harm the project - using the grids described below.

- Prioritisation: rank stakeholders on the assessed evidence, so engagement effort is proportionate to stake.

Engagement follows, and the results feed back: once engagement begins, the assessment is revised.

Help-harm potential

Every stakeholder has two distinct capacities in relation to the project:

•	Help potential: how much this stakeholder could contribute to success (resources, approvals, legitimacy, information, influence with others).

•	Harm potential: how much this stakeholder could damage or derail the project (blocking approvals, damaging reputation, mobilising opposition, withholding cooperation).

Help and harm are two independent capacities, not one attitude scale running from supportive to hostile. A stakeholder can be high on both - a powerful partner whose support is essential and whose displeasure is dangerous - and a stakeholder can be low on both. Judging stakeholders on a single "positive versus negative" axis hides exactly the cases that matter.

The potential matrix

The potential matrix compares help potential with harm potential for each stakeholder. It answers: where could support be mobilised, and where must harm be reduced or contained? Its output is not a ranking but a diagnosis of each stakeholder's capacity for effect, and it is the basis for deciding how much engagement effort each deserves.

The commitment matrix

The commitment matrix compares two different quantities:

•	Current commitment: how much the stakeholder is actually investing in the project today (attention, effort, resources, advocacy).

•	Required commitment: how much this stakeholder needs to invest for the project to succeed.

The difference between them is the commitment gap. The gap selects the engagement action: a large gap calls for deliberate engagement moves to raise commitment, a small gap calls for maintenance. After the engagement action, reassess - the matrix is a living picture, not a one-off score. Two cautions belong to the definition itself: commitment is not formal authority, not interest, and not technical expertise (a stakeholder can hold authority while investing nothing), and the required commitment is not identical for everyone.

CATWOE: reading a stakeholder's situation

CATWOE is a mnemonic for unpacking any stakeholder's view of the situation. It comes from systems thinking and is used in stakeholder analysis to surface what each party actually assumes:

| Letter | Stands for | The question it answers |
| --- | --- | --- |
| C | Customers (clients) | Who receives the output of the process, or suffers its consequences? |
| A | Actors | Who carries out the transformation, the people doing the work? |
| T | Transformation | What core process turns inputs into outputs, what changes? |
| W | Weltanschauung (worldview) | What worldview or assumption makes this transformation meaningful and worth doing? |
| O | Owner | Who owns or controls the process and could stop it? |
| E | Environment | What external constraints must be accepted as given (law, policy, market, environment)? |

Two stakeholders can agree on every fact and still disagree because their W differs: the same housing development is "recovery" under one worldview and "exclusion" under another. CATWOE makes that difference explicit instead of personal.

MoSCoW prioritisation

MoSCoW is a prioritisation method for sorting requirements, demands or engagement commitments by necessity:

•	Must have: critical; without it the project or the engagement fails.

•	Should have: important but not critical; painful to miss, but survivable with a workaround.

•	Could have: desirable; included if capacity allows.

•	Won't have (this time): consciously deferred or excluded, and recorded as such.

In stakeholder work MoSCoW turns a long list of stakeholder demands into an agreed order of attention, and the "won't have" category does real work: it converts silent neglect into an explicit, communicable decision.

Frameworks and Formulas

The combined two-matrix workflow

- Identify each stakeholder's role and impact.

- Assess help potential and harm potential.

- Compare current commitment with required commitment.

- Justify a role-specific engagement action from those two readings.

- Revise the assessment after the engagement feedback arrives.

Worked Examples

Reading the two matrices together (illustrative data)

Take three hypothetical stakeholders in a systems rollout:

| Stakeholder | Help potential | Harm potential | Current commitment | Required commitment | Reading and engagement action |
| --- | --- | --- | --- | --- | --- |
| A: head of the implementing department | High (owns the staff and the data) | High (could refuse to release either) | Low (busy with other work) | High | The largest gap and the largest stakes: engage closely, negotiate the resource release early, monitor frequently |
| B: a regulator with approval power | Low (adds no resources) | High (can stop the project) | Low (has not engaged) | Medium (needs to understand the design) | Harm control: brief them early and clearly, keep them informed, remove the surprise that turns review into objection |
| C: a well-connected user representative | Medium (legitimacy, peer communication) | Low (no formal power) | High (already volunteering) | Medium | Already past the required level: maintain, use their goodwill as a channel to other users, do not over-invest |

Notice the reasoning, not the numbers: help and harm are scored separately (A is high on both), the gap is measured against a stakeholder-specific requirement (C's required level is lower than A's), and each engagement action follows from the two readings rather than from the stakeholder's status alone. Any ratings in such a table are proposed analysis, to be replaced by evidence as it arrives.

From one aggregated entry to three different actions

A project records "school community" as a single stakeholder, with modest harm potential and modest required commitment. Disaggregated, it becomes: school principals (approval gatekeepers, high harm potential if they object), teachers (must deliver the change in class, high required commitment), and students (affected end users, low commitment but legitimate interests requiring representation). The single entry suggested one modest engagement action; the disaggregated picture produces three different ones - brief and secure the principals, resource the teachers, represent the students.