PMGT1865 Week 02

PMGT1865 Week 02 — Work Breakdown Structure, Network Planning and CPM

From Scope to a Schedule

A Work Breakdown Structure (WBS) is a hierarchical decomposition of the project's scope into deliverables and smaller components. A work package is a lowest-level component that can be estimated, assigned and monitored. Work packages describe the work to be delivered; schedule activities describe the actions needed to deliver it.

A practical scheduling process is:

- Define the scope and decompose it into work packages and activities.

- Identify the logical dependencies between activities.

- Estimate activity durations using the available information and resource assumptions.

- Calculate the network's timing, project duration and scheduling flexibility.

- Present the schedule, check its resource feasibility and maintain it as conditions change.

An activity dependency specifies how one activity constrains another. A predecessor comes before an activity in the relevant logical relationship; a successor is constrained by it. In a finish-to-start relationship with no lag, a successor cannot start until its predecessor finishes.

Schedule Representations

•	A precedence network represents activities and their logical relationships. In an activity-on-node network, each node represents an activity and arrows show dependencies.

•	A Gantt chart represents activities as horizontal bars on a time axis. It communicates start times, finish times, durations and overlaps.

•	An activity table records durations, predecessors and calculated timing values. It supports both network calculations and the construction of a Gantt chart.

Duration estimates may use comparable previous work, productivity rates, detailed work-package estimates or expert judgement. Estimates should state their units and assumptions. A logical network alone does not establish that sufficient people or equipment are available.

Critical Path Method

The Critical Path Method (CPM) calculates the earliest and latest permissible activity times in a dependency network. For a network with fixed durations, finish-to-start relationships and no lag, the longest start-to-finish path determines the earliest project completion time.

| Symbol or term | Definition |
| --- | --- |
| d | Activity duration, in the same time units as all schedule values |
| ES | Early start: earliest feasible activity start |
| EF | Early finish: earliest feasible activity finish |
| LS | Late start: latest start that preserves the calculated project finish |
| LF | Late finish: latest finish that preserves the calculated project finish |
| Total float | Time an activity can be delayed without delaying project completion, subject to the network logic |
| Critical path | A continuous start-to-finish path with no total float under the calculated schedule |

Use a time-zero convention: an activity starting at time 0 with duration 4 finishes at time 4. All values below are working days.

Forward Pass

Process activities from the start towards the finish:

•	An unconstrained starting activity has ES = 0.

•	ES = max(EF of all immediate predecessors).

•	EF = ES + d.

•	The project duration is the largest EF among terminal activities.

The maximum is required because every predecessor must be complete before a finish-to-start successor can begin.

Backward Pass

Process activities from the finish towards the start:

•	Set the LF of each terminal activity to the project finish time.

•	LF = min(LS of all immediate successors).

•	LS = LF − d.

The minimum preserves every successor's latest allowable start.

Total Float and Interpretation

Total float = LS − ES = LF − EF.

Activities with zero total float form the critical path or paths. A delay to a critical activity delays project completion unless another change compensates for it. Positive total float is shared schedule flexibility, not permission to ignore dependencies.

Worked Example — Five-Activity CPM Network

All relationships are finish-to-start with zero lag. Activity A starts the project; E finishes it.

| Activity | Duration | Immediate predecessors |
| --- | --- | --- |
| A | 4 | None |
| B | 3 | A |
| C | 2 | A |
| D | 4 | B |
| E | 3 | C, D |

Step 1: Calculate the Forward Pass

| Activity | ES calculation | ES | EF = ES + d |
| --- | --- | --- | --- |
| A | Project start | 0 | 0 + 4 = 4 |
| B | EF of A | 4 | 4 + 3 = 7 |
| C | EF of A | 4 | 4 + 2 = 6 |
| D | EF of B | 7 | 7 + 4 = 11 |
| E | max(6, 11) | 11 | 11 + 3 = 14 |

The earliest project finish is day 14.

Step 2: Calculate the Backward Pass

| Activity | LF calculation | LF | LS = LF − d |
| --- | --- | --- | --- |
| E | Project finish | 14 | 14 − 3 = 11 |
| D | LS of E | 11 | 11 − 4 = 7 |
| C | LS of E | 11 | 11 − 2 = 9 |
| B | LS of D | 7 | 7 − 3 = 4 |
| A | min(LS of B, LS of C) = min(4, 9) | 4 | 4 − 4 = 0 |

Step 3: Calculate Float and Identify the Critical Path

| Activity | ES | EF | LS | LF | Total float = LS − ES |
| --- | --- | --- | --- | --- | --- |
| A | 0 | 4 | 0 | 4 | 0 |
| B | 4 | 7 | 4 | 7 | 0 |
| C | 4 | 6 | 9 | 11 | 5 |
| D | 7 | 11 | 7 | 11 | 0 |
| E | 11 | 14 | 11 | 14 | 0 |

The critical path is A → B → D → E, with duration 4 + 3 + 4 + 3 = 14 days. The other path, A → C → E, has duration 4 + 2 + 3 = 9 days. Activity C therefore has 5 days of total float.

Step 4: Translate the Earliest Schedule into Gantt Intervals

| Activity | Start | Finish |
| --- | --- | --- |
| A | 0 | 4 |
| B | 4 | 7 |
| C | 4 | 6 |
| D | 7 | 11 |
| E | 11 | 14 |

Each row can be drawn as a horizontal bar from its start to its finish. B and C overlap because both follow A and neither depends on the other.