PMGT1865 Week 03

PMGT1865 Week 03 — Overlapping Networks, Lag and Lead

Activities and Timing

A precedence network represents activities and the timing constraints between them. Overlapping relationships allow a successor to start before its predecessor finishes when the work logic permits this. They can model phased handovers, coordinated starts and coordinated finishes more accurately than finish-to-start links alone.

An activity box normally records its name, duration, early start, early finish, late start, late finish and total float.

| Symbol | Meaning |
| --- | --- |
| i, j | Predecessor activity i and successor activity j |
| dᵢ, dⱼ | Durations of activities i and j |
| ES, EF | Early start and early finish |
| LS, LF | Late start and late finish |
| ESD, EFD | Early start date and early finish date; equivalent timing concepts to ES and EF |
| L | Signed lag attached to a relationship |
| wᵢⱼ | Minimum separation between the starts of i and j implied by a relationship |

For each activity, EF = ES + d and LF = LS + d. All timing values must use consistent calendars and units.

Lag, Lead and Float

•	Lag is a required delay between the events connected by a relationship. A positive L delays the constrained successor event.

•	Lead allows the constrained successor event to occur earlier; it can be represented as a negative lag.

•	Slack, or total float, is scheduling flexibility: total float = LS − ES = LF − EF. It is calculated from the whole network rather than inserted as a relationship delay.

Four Relationship Types

FS, SS, FF and SF are also written FTS, STS, FTF and STF. A relationship gives a lower bound on the successor's timing, not necessarily its final scheduled time: other constraints may require a later start.

| Relationship | Meaning | Forward-pass constraint | Equivalent lower bound on ESⱼ |
| --- | --- | --- | --- |
| Finish-to-start: FS / FTS | j cannot start until L time units after i finishes | ESⱼ ≥ EFᵢ + L | ESᵢ + dᵢ + L |
| Start-to-start: SS / STS | j cannot start until L time units after i starts | ESⱼ ≥ ESᵢ + L | ESᵢ + L |
| Finish-to-finish: FF / FTF | j cannot finish until L time units after i finishes | EFⱼ ≥ EFᵢ + L | ESᵢ + dᵢ + L − dⱼ |
| Start-to-finish: SF / STF | j cannot finish until L time units after i starts | EFⱼ ≥ ESᵢ + L | ESᵢ + L − dⱼ |

For FF and SF, convert the finish constraint to a start constraint by subtracting the successor's duration. With multiple relationships, use the maximum of all applicable lower bounds and any project-start constraint.

Compound SS and FF Constraints

Both relationships can apply to the same activity pair. The successor must satisfy both:

ESⱼ = max(ESᵢ + Lₛₛ, EFᵢ + L𝒻𝒻 − dⱼ), subject to any other constraints.

Here Lₛₛ is the SS lag and L𝒻𝒻 is the FF lag. One relationship controls the early timing if its lower bound is larger; both control when the bounds are equal.

Forward and Backward Calculation Method

- Establish the relationships, durations, signed lags and project start.

- Convert every relationship to ESⱼ ≥ ESᵢ + wᵢⱼ using the table above.

- In the forward pass, set each ES to the largest applicable lower bound, then calculate EF = ES + d.

- Set the project finish to the largest required terminal EF.

- In the backward pass, each relationship requires LSᵢ ≤ LSⱼ − wᵢⱼ. Take the minimum applicable upper bound, including any required project-finish constraint.

- Calculate LF = LS + d and total float = LS − ES.

In a simple acyclic network with fixed durations, the controlling chain of tight relationships determines the project finish. With overlaps, adding the full durations of all activities on that chain can double-count overlapping time. Relationship offsets and lags must remain in the calculation.

Worked Example — Mixed FF, SS and FS Relationships

All durations and lags are in days. The project starts at time 0. A relationship without an explicit lag has zero lag.

| Activity | Duration | Predecessor relationship |
| --- | --- | --- |
| A | 15 | None |
| B | 5 | A FF + 3 |
| C | 2 | A SS + 10 |
| D | 8 | B FS + 2 |
| E | 5 | C FS |
| F | 10 | D FS and E FS |

Step 1: Forward Pass

| Activity | Calculation | ES | EF |
| --- | --- | --- | --- |
| A | ES = 0; EF = 0 + 15 | 0 | 15 |
| B | EF = 15 + 3 = 18; ES = 18 − 5 | 13 | 18 |
| C | ES = 0 + 10; EF = 10 + 2 | 10 | 12 |
| D | ES = 18 + 2; EF = 20 + 8 | 20 | 28 |
| E | ES = 12; EF = 12 + 5 | 12 | 17 |
| F | ES = max(28, 17); EF = 28 + 10 | 28 | 38 |

B starts before A finishes because the relationship constrains B's finish, not its start. The project finishes at day 38.

Step 2: Backward Pass

Start with F: LF = 38 and LS = 38 − 10 = 28.

| Activity | Backward constraint | LS | LF |
| --- | --- | --- | --- |
| F | Project finish = 38 | 28 | 38 |
| D | LF = LS of F = 28; LS = 28 − 8 | 20 | 28 |
| E | LF = LS of F = 28; LS = 28 − 5 | 23 | 28 |
| B | LF = LS of D − 2 = 18; LS = 18 − 5 | 13 | 18 |
| C | LF = LS of E = 23; LS = 23 − 2 | 21 | 23 |
| A | FF to B: LS ≤ 18 − 3 − 15 = 0; SS to C: LS ≤ 21 − 10 = 11; take min(0, 11) | 0 | 15 |

Step 3: Float and Critical Chain

| Activity | ES | EF | LS | LF | Total float |
| --- | --- | --- | --- | --- | --- |
| A | 0 | 15 | 0 | 15 | 0 |
| B | 13 | 18 | 13 | 18 | 0 |
| C | 10 | 12 | 21 | 23 | 11 |
| D | 20 | 28 | 20 | 28 | 0 |
| E | 12 | 17 | 23 | 28 | 11 |
| F | 28 | 38 | 28 | 38 | 0 |

The critical path is A → B → D → F. Its controlling timing is 15 days to A's finish, 3 days to B's finish, 2 days of lag before D, 8 days for D and 10 days for F:

15 + 3 + 2 + 8 + 10 = 38 days.

B's full five-day duration is not added again because its start overlaps A. C and E each have 11 days of total float; this is shared flexibility on their branch rather than 22 independent days.