PMGT1865 Week 04

PMGT1865 Week 04 — PERT and Duration Uncertainty

Purpose and Three-Point Estimates

The Program Evaluation and Review Technique (PERT) uses three estimates of each activity's duration to represent uncertainty and approximate the probability of finishing within a target duration.

| Symbol | Definition |
| --- | --- |
| a | Optimistic duration: a favourable estimate |
| m | Most likely duration: the estimate judged most probable |
| b | Pessimistic duration: an unfavourable estimate |
| tₑ | Expected activity duration |
| σᵢ | Estimated standard deviation of activity i's duration |
| σᵢ² | Estimated variance of activity i's duration |
| μ | Expected duration of the selected critical path |
| σₚ | Standard deviation of that path's total duration |
| T | Target elapsed completion time |
| z | Target's distance from the expected duration in standard-deviation units |
| Φ(z) | Standard normal cumulative probability up to z |

Use consistent time units and estimates satisfying a ≤ m ≤ b. Variance has squared time units; standard deviation has the same time units as duration.

Activity and Project Formulas

| Quantity | Formula |
| --- | --- |
| Expected activity duration | tₑ = (a + 4m + b) ÷ 6 |
| Activity standard deviation | σᵢ = (b − a) ÷ 6 |
| Activity variance | σᵢ² = ((b − a) ÷ 6)² |
| Expected critical-path duration | μ = Σ tₑ along the selected critical path |
| Critical-path variance, assuming independent durations | σₚ² = Σ σᵢ² along that path |
| Critical-path standard deviation | σₚ = √(Σ σᵢ²) |
| Standardised target | z = (T − μ) ÷ σₚ |
| Approximate completion probability | P(completion by T) ≈ Φ(z) |

The sum symbol Σ means to add the indicated values. The project mean is also sometimes written TE; tₑ refers to an individual activity here.

•	A positive z means the target is later than the expected duration.

•	A negative z means it is earlier.

•	z = 0 corresponds to approximately 50% completion probability under the normal approximation.

•	A target time for probability p can be estimated as T = μ + zₚσₚ, where Φ(zₚ) = p.

Calculation Method

- Define the network and obtain a, m and b for every activity.

- Calculate each expected duration and variance.

- Use the expected durations in a critical-path calculation. The critical path is the longest logical start-to-finish path for those durations.

- Add expected durations and variances along that path, then take the square root of the variance sum.

- Calculate z for the target time and evaluate Φ(z).

- Interpret the probability in light of the independence, path-selection and distribution assumptions.

Keep full precision until the final display unless deliberately demonstrating a specified rounding convention.

Worked Example — Three Activities and a 14-Day Target

A precedes both B and C, with finish-to-start links and zero lag. The project completes only after both branches finish. All duration estimates are in days.

Step 1: Calculate Activity Estimates

| Activity | a | m | b | Expected duration tₑ | Standard deviation | Variance |
| --- | --- | --- | --- | --- | --- | --- |
| A | 3 | 5 | 9 | (3 + 4 × 5 + 9) ÷ 6 = 32/6 = 5.3333 | (9 − 3) ÷ 6 = 1 | 1 |
| B | 4 | 6 | 10 | (4 + 4 × 6 + 10) ÷ 6 = 38/6 = 6.3333 | (10 − 4) ÷ 6 = 1 | 1 |
| C | 2 | 4 | 8 | (2 + 4 × 4 + 8) ÷ 6 = 26/6 = 4.3333 | (8 − 2) ÷ 6 = 1 | 1 |

The decimal values shown are rounded for display; calculations below use the fractions.

Step 2: Compare the Paths

| Path | Expected duration |
| --- | --- |
| A → B | 32/6 + 38/6 = 70/6 = 11.6667 days |
| A → C | 32/6 + 26/6 = 58/6 = 9.6667 days |

A → B is the critical path based on expected durations. Thus μ = 70/6 ≈ 11.67 days.

Step 3: Calculate Project Uncertainty

For A → B:

•	σₚ² = 1 + 1 = 2 days².

•	σₚ = √2 ≈ 1.4142 days.

C's variance is not included in this selected-path approximation. This does not mean that uncertainty on the other branch can never affect actual completion.

Step 4: Calculate the Completion Probability

For T = 14 days:

z = (14 − 70/6) ÷ √2 ≈ 1.6499.

Φ(1.6499) ≈ 0.95052, giving an approximate 95.05% probability of completing by day 14 under the selected-path normal approximation. A normal table using z rounded to 1.65 gives approximately 95.05% as well.

Strengths and Limitations

•	Three-point estimates make uncertainty explicit rather than hiding it inside a single duration.

•	The formulas support a structured comparison of completion targets and schedule risk.

•	The estimates remain judgement-dependent; optimistic and pessimistic durations are not guaranteed bounds.

•	Adding variances assumes independent activity durations. Shared causes can make durations correlated.

•	A normal approximation may be weak for short paths or strongly skewed durations.

•	A non-critical or near-critical branch may become the longest path when actual durations vary. A fixed-path approximation can therefore overstate completion probability.

•	Resource constraints, calendar restrictions and changing dependencies require additional schedule modelling; the probability calculation does not resolve them automatically.